## Project Management Plan
Week | Deliverable | Release
2020-10-01 | Setup Git hub Repo
2020-10-08 | Create project structure - Makefile, requirements.txt, hello.py, test_hello.py
2020-10-15 | Implement code in hello.py, test_hello.py
2020-10-22 | Implement Makefile
2020-10-29 | Populate requirement.txt. Verify all targets in Makefile function correctly | 1
2020-11-05 | Analyze feasibility of Github Actions
2020-11-12 | Configure Github Actions -1
2020-11-19 | Configure Github Actions -2
2020-11-26 | Deliver Continuous Integration | 2
2020-12-03 | Create Azure Web App
2020-12-10 | Configure Azure Pipeline with self-hosted agent
2020-12-17 | Deliver Continuous Delivery Pipeline to deploy Azure web app | 3
| Quarterly Goals | Proposed Difficulty(1- easy, 3- tough) | Yearly Goals | Proposed Difficulty(1- easy, 3- tough)
Q1 | Configure Github actions trigger for every pull request - Phase 1 | 2 | For every pull request, Continuous Integration pipeline should all the integration tests in addition to build, unit tests and quality checks | 3
Q2 | Configure Github actions trigger for every pull request - Phase 2 | 2
Q3 | Implement test bed to perform complete integration testing as part of CI/CD pipeline to prevent regressions - Phase 1 | 3
Q4 | Implement test bed to perform complete integration testing as part of CI/CD pipeline to prevent regressions - Phase 2 | 3